## Test plan
Info |  | Variables
Name | Done | Belt tension Motor[ | Speed(RPM)[800,1300,1800] | Load(Current)
1 | X | 225 | 800 | 18
2 | X |  |  | 20
3 | X |  |  | 22
4 | X |  | 1300 | 18
5 | X |  |  | 20
6 | X |  |  | 22
7 | X |  | 1800 | 18
8 | X |  |  | 20
9 | X |  |  | 22
10 |  | 190 | 800 | 18
11 |  |  |  | 20
12 |  |  |  | 22
13 |  |  | 1300 | 18
14 |  |  |  | 20
15 |  |  |  | 22
16 |  |  | 1800 | 18
17 |  |  |  | 20
18 |  |  |  | 22

## Test plan 2
Info |  | Variables
Name | Done | Belt tension Motor[ | Speed(RPM)[800,1300,1800] | Load(Current) | Compressor status
1 |  | 180 | 810 | 18 | On
2 |  |  |  | 20
3 |  |  |  | 22
4 |  |  | 1320 | 18
5 |  |  |  | 20
6 |  |  |  | 22
7 |  |  | 1800 | 18
8 |  |  |  | 20
9 |  |  |  | 22

## Tests 2018-04-20
Sheet for entering test data
Info |  |  | Variables |  |  |  | Parameters
Date | Duration | Name | Belt tension Motor(Pound-force) | Speed(RPM) | Load(Current) |  | Belt tension Compressor(Pound-force) | Belt tension Motor low | VFD Frequency(Hz) | Note
2018-04-20 , 13:48 | 18:55 | 1 | 225 | 800 | 17.6 |  | - | - | 27
2018-04-20 , 14:05 | 13:00 | 2 | 225 | 800 | 20.2 |  |  |  | 27
2018-04-20,14:18 | ? | 3 | 225 | 800 | 23.6 |  |  |  | 27
2018-04-20,14:33 | 14:30 | 4 | 225 | 1300 | 18 |  |  |  | 44
| 8:00 | 5 | 225 | 1300 | 20.2 |  |  |  | 44
| 13:00 | 6 | 225 | 1300 | 21.9 |  |  |  | 44
|  | 7 | 225 | 1800 |  |  |  |  | 60
8
9
10
11
12
13
14
15
16
17
18
T2 |  |  | T3 |  |  | T4 |  |  | T5 |  | T6 |  | T7 |  | T8 |  | T9
5 | 20.6 |  | 0 | 21.1 |  | 0 | 23.6 |  | 0 | 18.2 | 0 | 20.3 | 0 | 22 | 0 | 18.1 | 0 | 20.8
5.5 | 20.7 |  | 0.5 | 21.1 |  | 0.5 |  |  | 0.5 | 18.5 | 0.5 | 20.7 | 0.5 |  | 0.5 | 19.3 | 0.5 | 20.5
6 | 20.7 |  | 1 | 21.1 |  | 1 | 16.8 |  | 1 | 18.9 | 1 | 21.2 | 1 | 16.8 | 1 | 19.4 | 1 | 17.6
6.5 | 20.7 |  | 1.5 | 22 |  | 1.5 | 19.5 |  | 1.5 | 18.9 | 1.5 | 22 | 1.5 | 19.5 | 1.5 | 19.8 | 1.5 | 17.7
7 | 20.7 |  | 2 | 22.4 |  | 2 | 19.5 |  | 2 | 19.8 | 2 | 22 | 2 | 18.2 | 2 | 19.8 | 2 | 21.6
7.5 | 20.8 |  | 2.5 | 22.4 |  | 2.5 | 19 |  | 2.5 | 19.8 | 2.5 | 22.3 | 2.5 | 18.1 | 2.5 | 19.8 | 2.5 | 21.2
8 | 21 |  | 3 | 22.8 |  | 3 | 19.4 |  | 3 | 20.2 | 3 | 22.4 | 3 | 18.5 | 3 | 20.2 | 3 | 21.1
8.5 | 21.1 |  | 3.5 | 22.8 |  | 3.5 |  |  | 3.5 | 20.2 | 3.5 | 22.8 | 3.5 | 18.5 | 3.5 | 20.2 | 3.5 | 21.5
9 | 21.1 |  | 4 | 22.9 |  | 4 | 18.5 |  | 4 | 20.3 | 4 | 22.8 | 4 | 18.1 | 4 | 20.2 | 4 | 21
9.5 | 21.1 |  | 4.5 | 23.2 |  | 4.5 | 18.1 |  | 4.5 | 20.6 | 4.5 | 22.8 | 4.5 | 18.1 | 4.5 | 20.2 | 4.5 | 16.4
10 |  |  | 5 | 23.2 |  | 5 | 18.1 |  | 5 | 20.5 | 5 | 23.2 | 5 | 18.5 | 5 | 20.6 | 5 | 18
10.5 |  |  | 5.5 | 23.2 |  | 5.5 | 18.1 |  | 5.5 | 20.3 | 5.5 | 23.2 | 5.5 | 18.3 | 5.5 | 20.6 | 5.5 | 21.1
11 | 21.1 |  | 6 | 23.3 |  | 6 | 18.1 |  | 6 | 20.6 | 6 | 22.8 | 6 | 18.1 | 6 | 20.6 | 6 | 21.1
11.5 |  |  | 6.5 | 23.6 |  | 6.5 | 18.1 |  | 6.5 | 20.2 | 6.5 | 22.7 | 6.5 | 18.5 | 6.5 | 20.6 | 6.5 | 21.1
12 |  |  | 7 | 23.7 |  | 7 | 18.1 |  | 7 | 20.2 | 7 | 22.4 | 7 | 18.4 | 7 | 20.7 | 7 | 21.1
12.5 |  |  | 7.5 | 23.6 |  | 7.5 | 18.1 |  | 7.5 | 20.2 | 7.5 | 22.4 | 7.5 | 18.1 | 7.5 | 20.7 | 7.5 | 21.5
13 | 21.1 |  | 8 | 23.6 |  | 8 | 18.1 |  | 8 | 20.2 | 8 | 22.4 | 8 | 18.1 | 8 | 20.7 | 8 | 21.5
13.5 |  |  | 8.5 |  |  | 8.5 | 18 |  | 8.5 |  | 8.5 | 22.4 | 8.5 | 18.1 | 8.5 | 20.7 | 8.5 | 21.1
14 |  |  | 9 | 23.7 |  | 9 | 18 |  | 9 |  | 9 | 22.2 | 9 | 18.1 | 9 | 20.7 | 9 | 21.1
14.5 |  |  | 9.5 | 24 |  | 9.5 | 18.1 |  | 9.5 |  | 9.5 | 22 | 9.5 | 18.1 | 9.5 |  | 9.5 | 21.1
15 |  |  | 10 | 23.7 |  | 10 | 18.1 |  | 10 |  | 10 | 22 | 10 | 18.5 | 10 |  | 10 | 21.1
15.5 |  |  | 10.5 | 23.2 |  | 10.5 | 18.1 |  | 10.5 |  | 10.5 | 21.9 |  |  |  |  | 10.5 | 21.1
16 |  |  | 11 | 23.2 |  | 11 | 18.1 |  | 11 |  | 11 | 21.9 |  |  |  |  | 11 | 21.1
|  |  | 11.5 | 23.2 |  | 11.5 | 18.1 |  | 11.5 |  | 11.5 | 21.9 |  |  |  |  | 11.5 | 21.1
|  |  | 12 | 23.2 |  | 12 | 18.1 |  | 12 |  | 12 | 22 |  |  |  |  | 12 | 21.1
|  |  | 12.5 |  |  | 12.5 | 17.9 |  | 12.5 |  | 12.5 | 21.9 |  |  |  |  | 12.5
|  |  | 13 |  |  | 13 | 17.9 |  | 13 |  | 13 | 21.9 |  |  |  |  | 13
|  |  | 13.5 |  |  | 13.5 | 17.8 |  | 13.5 |  | 13.5 | [5 empty] | 13.5
[6 empty] | 14 | 18 |  | 14 |  | 14 | [5 empty] | 14
[6 empty] | 14.5 | [10 empty] | 14.5
[6 empty] | 15 | [10 empty] | 15
15.5

## Tests 2018-04-24
Name | Tensioned | Done | Belt tension Motor(+-10) | Speed(RPM) | Load(Current) | Compressor | Tension after test | Measured tension | Comment
| Very Loose | X | 100 | 810 | 10 | Off | 125 | 100
| Loose | / | 120 | 810 | 10 | Off |  | 122.6 | 180deg
| Normal |  | 140 | 810 | 10 | Off |  | ~140 | 180deg
| Tensioned |  | 160 | 810 | 10 | Off |  | ~160 | 180deg
| Very Tensioned |  | 180 | 810 | 10 | Off |  | 170-180
| Tests for T1-T12_steady/trans_t95-t180 |  |  | 2018-04-24

## Tests 2018-04-26
2018-04-26 | Name | Test.nr | Description | T | T_after | I | RPM[840,1200,1590] | Heat from roof
| Warm up | 0 | Warm up test with compressor initally off, then turned on, 24 Ampere, 810 RPM, 170-180 tension | 175 | 175-185 | 0-24 | 0-810
am | T1_t200_i24_rpm1600 | 1 | Test for high tension with compressor on, from warmed up to steady state, change current to 21 in name, long run to determine the top temperature of tensioner pulley, adjusted fan power | 180-200 |  | 21-22 | 1590
| T2_t200_i24_rpm1200 | 2 | Reduced speed, same setup | 180-200 |  | 22-23 | 1200
| T3_t200_i24_rpm800 | 3 | Reduced speed, same setup, and cooldown in same test | 180-200 | 200 | 23 | 840
pm | T4_t100_i24_rpm1600 | 4 | Same as test 1 but with 100 in tension, start from cold(2 hours lunch) | 100 |  | 22 | 1590
| T5_t100_i24_rpm1200 | 5 | from test 4, compressor off, decreasing speed to 1200, then compressor on, door opened after 7mins, 14:30 roof heat turned down | 100 |  | 23 | 1200
| T6_t100_i24_rpm800 | 6 | from test 5, compressor off, decreasing speed to 800, then compressor on, compressor off from 13:25, ramp down | 100 | 130 | 23 | 840

## Tests 2018-04-27
2018-04-27 | Name | Test.nr | Description | T | T_after | T_Comp | T_after_comp | I | RPM[840,1200,1590] | hz
| Warm up | 0 | Tensioned to 200, running for 20 minutes, ramp down,stop, 2,5 turns cw | 200 | 200 |  | 220 |  | 0-1500
am | T7_t75_i24_rpm800 | 7 | 3 turns a-cw (100-110), 1 turn extra a-cw(80-90), another 0,5 a-cw(75), ramp up without load, fans on 4:20, comp on 4:40, door opens 11:00, changing load for a period, cooldown | 75 | 78,79,70,77,80 |  | 100 | 21-22 | 840 | 28
| T8_t75_i24_rpm800_noLoad | 8 | No load, same as before | 75 | 75 | 100 | 100 | 9.0-10.0 | 840 | 28
| T9_t75_i24_rpm1200 | 9 | No load, same as before, ramp down lunch break | 75 | 75 | 100 | 100 | 9 | 1200
pm | T10_t75_i24_rpm1600 | 10 | No load |  |  |  |  | 9.0-10 | 1600
| test1200Load | 9_2 | added load from 120 rpm without load, removed load, cooldown | 75 | 75 | 100 | 100 | 23
| T11_t300_i24_rpm1600 | 11 | 5 turns cw(230),2 turn cw(250), 1 turn cw(250), 1turn cw(), 0.5 turn a-cw(310,370), 0.5 a-cw. , ramp up then load on | 300 |  | 360 |  | 22 | 1590
| T12_t300_i24_rpm1200 | 12 | ramp down to 1200 from 1600, clutch off and on | 300 |  | 360 |  | 23 | 1200
| T13_t300_i24_rpm800 | 13 | same as T12, pulley temperature strange in 03:40:00 clutch off/ on/ off, ramp down | 300 | 250 | 360 | 260 | 23 | 840

## Changes to rig and DAQ
2018-04-27 | 14:38 | moved thermo couple on pulley
| 15:09 | card board is loose, warm air enters compressor area
| 15:41 | card borad back in place