## Test plan
Info |  | Variables
Name | Done | Belt tension Motor[ | Speed(RPM)[800,1300,1800] | Load(Current)
1 | X | 225 | 800 | 18
2 | X |  |  | 20
3 | X |  |  | 22
4 | X |  | 1300 | 18
5 | X |  |  | 20
6 | X |  |  | 22
7 | X |  | 1800 | 18
8 | X |  |  | 20
9 | X |  |  | 22
10 |  | 190 | 800 | 18
11 |  |  |  | 20
12 |  |  |  | 22
13 |  |  | 1300 | 18
14 |  |  |  | 20
15 |  |  |  | 22
16 |  |  | 1800 | 18
17 |  |  |  | 20
18 |  |  |  | 22

## Test plan 2
Info |  | Variables
Name | Done | Belt tension Motor[ | Speed(RPM)[800,1300,1800] | Load(Current) | Compressor status
1 |  | 180 | 810 | 18 | On
2 |  |  |  | 20
3 |  |  |  | 22
4 |  |  | 1320 | 18
5 |  |  |  | 20
6 |  |  |  | 22
7 |  |  | 1800 | 18
8 |  |  |  | 20
9 |  |  |  | 22

## Tests 2018-04-20
Sheet for entering test data
Info |  |  | Variables |  |  |  | Parameters
Date | Duration | Name | Belt tension Motor(Pound-force) | Speed(RPM) | Load(Current) |  | Belt tension Compressor(Pound-force) | Belt tension Motor low | VFD Frequency(Hz) | Note
2018-04-20 , 13:48 | 18:55 | 1 | 225 | 800 | 17.6 |  | - | - | 27
2018-04-20 , 14:05 | 13:00 | 2 | 225 | 800 | 20.2 |  |  |  | 27
2018-04-20,14:18 | ? | 3 | 225 | 800 | 23.6 |  |  |  | 27
2018-04-20,14:33 | 14:30 | 4 | 225 | 1300 | 18 |  |  |  | 44
| 8:00 | 5 | 225 | 1300 | 20.2 |  |  |  | 44
| 13:00 | 6 | 225 | 1300 | 21.9 |  |  |  | 44
|  | 7 | 225 | 1800 |  |  |  |  | 60
8
9
10
11
12
13
14
15
16
17
18
T2 |  |  | T3 |  |  | T4 |  |  | T5 |  | T6 |  | T7 |  | T8 |  | T9
5 | 20.6 |  | 0 | 21.1 |  | 0 | 23.6 |  | 0 | 18.2 | 0 | 20.3 | 0 | 22 | 0 | 18.1 | 0 | 20.8
5.5 | 20.7 |  | 0.5 | 21.1 |  | 0.5 |  |  | 0.5 | 18.5 | 0.5 | 20.7 | 0.5 |  | 0.5 | 19.3 | 0.5 | 20.5
6 | 20.7 |  | 1 | 21.1 |  | 1 | 16.8 |  | 1 | 18.9 | 1 | 21.2 | 1 | 16.8 | 1 | 19.4 | 1 | 17.6
6.5 | 20.7 |  | 1.5 | 22 |  | 1.5 | 19.5 |  | 1.5 | 18.9 | 1.5 | 22 | 1.5 | 19.5 | 1.5 | 19.8 | 1.5 | 17.7
7 | 20.7 |  | 2 | 22.4 |  | 2 | 19.5 |  | 2 | 19.8 | 2 | 22 | 2 | 18.2 | 2 | 19.8 | 2 | 21.6
7.5 | 20.8 |  | 2.5 | 22.4 |  | 2.5 | 19 |  | 2.5 | 19.8 | 2.5 | 22.3 | 2.5 | 18.1 | 2.5 | 19.8 | 2.5 | 21.2
8 | 21 |  | 3 | 22.8 |  | 3 | 19.4 |  | 3 | 20.2 | 3 | 22.4 | 3 | 18.5 | 3 | 20.2 | 3 | 21.1
8.5 | 21.1 |  | 3.5 | 22.8 |  | 3.5 |  |  | 3.5 | 20.2 | 3.5 | 22.8 | 3.5 | 18.5 | 3.5 | 20.2 | 3.5 | 21.5
9 | 21.1 |  | 4 | 22.9 |  | 4 | 18.5 |  | 4 | 20.3 | 4 | 22.8 | 4 | 18.1 | 4 | 20.2 | 4 | 21
9.5 | 21.1 |  | 4.5 | 23.2 |  | 4.5 | 18.1 |  | 4.5 | 20.6 | 4.5 | 22.8 | 4.5 | 18.1 | 4.5 | 20.2 | 4.5 | 16.4
10 |  |  | 5 | 23.2 |  | 5 | 18.1 |  | 5 | 20.5 | 5 | 23.2 | 5 | 18.5 | 5 | 20.6 | 5 | 18
10.5 |  |  | 5.5 | 23.2 |  | 5.5 | 18.1 |  | 5.5 | 20.3 | 5.5 | 23.2 | 5.5 | 18.3 | 5.5 | 20.6 | 5.5 | 21.1
11 | 21.1 |  | 6 | 23.3 |  | 6 | 18.1 |  | 6 | 20.6 | 6 | 22.8 | 6 | 18.1 | 6 | 20.6 | 6 | 21.1
11.5 |  |  | 6.5 | 23.6 |  | 6.5 | 18.1 |  | 6.5 | 20.2 | 6.5 | 22.7 | 6.5 | 18.5 | 6.5 | 20.6 | 6.5 | 21.1
12 |  |  | 7 | 23.7 |  | 7 | 18.1 |  | 7 | 20.2 | 7 | 22.4 | 7 | 18.4 | 7 | 20.7 | 7 | 21.1
12.5 |  |  | 7.5 | 23.6 |  | 7.5 | 18.1 |  | 7.5 | 20.2 | 7.5 | 22.4 | 7.5 | 18.1 | 7.5 | 20.7 | 7.5 | 21.5
13 | 21.1 |  | 8 | 23.6 |  | 8 | 18.1 |  | 8 | 20.2 | 8 | 22.4 | 8 | 18.1 | 8 | 20.7 | 8 | 21.5
13.5 |  |  | 8.5 |  |  | 8.5 | 18 |  | 8.5 |  | 8.5 | 22.4 | 8.5 | 18.1 | 8.5 | 20.7 | 8.5 | 21.1
14 |  |  | 9 | 23.7 |  | 9 | 18 |  | 9 |  | 9 | 22.2 | 9 | 18.1 | 9 | 20.7 | 9 | 21.1
14.5 |  |  | 9.5 | 24 |  | 9.5 | 18.1 |  | 9.5 |  | 9.5 | 22 | 9.5 | 18.1 | 9.5 |  | 9.5 | 21.1
15 |  |  | 10 | 23.7 |  | 10 | 18.1 |  | 10 |  | 10 | 22 | 10 | 18.5 | 10 |  | 10 | 21.1
15.5 |  |  | 10.5 | 23.2 |  | 10.5 | 18.1 |  | 10.5 |  | 10.5 | 21.9 |  |  |  |  | 10.5 | 21.1
16 |  |  | 11 | 23.2 |  | 11 | 18.1 |  | 11 |  | 11 | 21.9 |  |  |  |  | 11 | 21.1
|  |  | 11.5 | 23.2 |  | 11.5 | 18.1 |  | 11.5 |  | 11.5 | 21.9 |  |  |  |  | 11.5 | 21.1
|  |  | 12 | 23.2 |  | 12 | 18.1 |  | 12 |  | 12 | 22 |  |  |  |  | 12 | 21.1
|  |  | 12.5 |  |  | 12.5 | 17.9 |  | 12.5 |  | 12.5 | 21.9 |  |  |  |  | 12.5
|  |  | 13 |  |  | 13 | 17.9 |  | 13 |  | 13 | 21.9 |  |  |  |  | 13
|  |  | 13.5 |  |  | 13.5 | 17.8 |  | 13.5 |  | 13.5 | [5 empty] | 13.5
[6 empty] | 14 | 18 |  | 14 |  | 14 | [5 empty] | 14
[6 empty] | 14.5 | [10 empty] | 14.5
[6 empty] | 15 | [10 empty] | 15
15.5

## Tests 2018-04-24
Name | Tensioned | Done | Belt tension Motor(+-10) | Speed(RPM) | Load(Current) | Compressor | Tension after test | Measured tension | Comment
| Very Loose | X | 100 | 810 | 10 | Off | 125 | 100
| Loose | / | 120 | 810 | 10 | Off |  | 122.6 | 180deg
| Normal |  | 140 | 810 | 10 | Off |  | ~140 | 180deg
| Tensioned |  | 160 | 810 | 10 | Off |  | ~160 | 180deg
| Very Tensioned |  | 180 | 810 | 10 | Off |  | 170-180
| Tests for T1-T12_steady/trans_t95-t180 |  |  | 2018-04-24

## Tests 2018-04-26
2018-04-26 | Name | Test.nr | Description | T | T_after | I | RPM[840,1200,1590] | Heat from roof
| Warm up | 0 | Warm up test with compressor initally off, then turned on, 24 Ampere, 810 RPM, 170-180 tension | 175 | 175-185 | 0-24 | 0-810
am | T1_t200_i24_rpm1600 | 1 | Test for high tension with compressor on, from warmed up to steady state, change current to 21 in name, long run to determine the top temperature of tensioner pulley, adjusted fan power | 180-200 |  | 21-22 | 1590
| T2_t200_i24_rpm1200 | 2 | Reduced speed, same setup | 180-200 |  | 22-23 | 1200
| T3_t200_i24_rpm800 | 3 | Reduced speed, same setup, and cooldown in same test | 180-200 | 200 | 23 | 840
pm | T4_t100_i24_rpm1600 | 4 | Same as test 1 but with 100 in tension, start from cold(2 hours lunch) | 100 |  | 22 | 1590
| T5_t100_i24_rpm1200 | 5 | from test 4, compressor off, decreasing speed to 1200, then compressor on, door opened after 7mins, 14:30 roof heat turned down | 100 |  | 23 | 1200
| T6_t100_i24_rpm800 | 6 | from test 5, compressor off, decreasing speed to 800, then compressor on, compressor off from 13:25, ramp down | 100 | 130 | 23 | 840

## Tests 2018-04-27
2018-04-27 | Name | Test.nr | Description | T | T_after | T_Comp | T_after_comp | I | RPM[840,1200,1590] | hz
| Warm up | 0 | Tensioned to 200, running for 20 minutes, ramp down,stop, 2,5 turns cw | 200 | 200 |  | 220 |  | 0-1500
am | T7_t75_i24_rpm800 | 7 | 3 turns a-cw (100-110), 1 turn extra a-cw(80-90), another 0,5 a-cw(75), ramp up without load, fans on 4:20, comp on 4:40, door opens 11:00, changing load for a period, cooldown | 75 | 78,79,70,77,80 |  | 100 | 21-22 | 840 | 28
| T8_t75_i24_rpm800_noLoad | 8 | No load, same as before | 75 | 75 | 100 | 100 | 9.0-10.0 | 840 | 28
| T9_t75_i24_rpm1200 | 9 | No load, same as before, ramp down lunch break | 75 | 75 | 100 | 100 | 9 | 1200
pm | T10_t75_i24_rpm1600 | 10 | No load |  |  |  |  | 9.0-10 | 1600
| test1200Load | 9_2 | added load from 120 rpm without load, removed load, cooldown | 75 | 75 | 100 | 100 | 23
| T11_t300_i24_rpm1600 | 11 | 5 turns cw(230),2 turn cw(250), 1 turn cw(250), 1turn cw(), 0.5 turn a-cw(310,370), 0.5 a-cw. , ramp up then load on | 300 |  | 360 |  | 22 | 1590
| T12_t300_i24_rpm1200 | 12 | ramp down to 1200 from 1600, clutch off and on | 300 |  | 360 |  | 23 | 1200
| T13_t300_i24_rpm800 | 13 | same as T12, pulley temperature strange in 03:40:00 clutch off/ on/ off, ramp down | 300 | 250 | 360 | 260 | 23 | 840

## Test 2018-05-01
| Name | Test.nr | Description | T | T_after | T_Comp | T_after_comp | I(from to) | RPM[840,1200,1590] | hz
| Warm up |  | tension same as Friday | 260 | - | - | - |  | 0-1500
am | T14_Ten75_LowLoad_AllRPM | 14 | trying all rpm with low load, exactly 30 seconds on each rpm level, 6 turns a-cw, one minute settle time, time 18:30, last 30 nothing | 75 | 80 |  |  | 22-19 | 810.:30.:1800
| T15_Ten75_HighLoad_AllRPM | 15 | trying all rpm with high load, around 30 seconds on each rpm level, 2,30 minute settle time, 30 sec stop time in end, 19:30 done, rest stop time | 80 | 90 | - | 105 | 25-22 | 810.:30.:1800
pm | test_after_pulley_changed |  | Service and disassembly, down 14 turns, warm up test, accelerometer on condeser fan casing |  | 180 |  | 200-205
| T16_Ten180_LowLoad_AllRPM | 16 | trying all rpm with low load,30 settle, around 30 seconds on each rpm level, one minute settle time, done 18:30, last 30 nothing | 180 | 185 | 200-205 | 205 | 22-19 | 810.:30.:1800
| T17_Ten180_HighLoad_AllRPM | 17 | trying all rpm with high load, 2 settling time, around 30 seconds on each rpm level, one minute settle time(?), done 19, last 30 nothing | 185 | 190 | 205 | 210 | 25-22 | 810.:30.:1800
| T18_Ten300_LowLoad_AllRPM | 18 | up 4 turns, 60 seconds settle, done 18(comp off), cooldown 30 | 300 | 290 | 350 | 330 | 22-19 | 810.:30.:1800
| T19_Ten300_HighLoad_AllRPM | 19 | 2.30 seconds settle, done 19(compressor off), cooldown 30 seconds | 290 | 280 | 330 | 325 | 25-21 | 810.:30.:1800

## Test2018-05-03
Name | Test.nr | Description | T | T_after | T_Comp | T_after_comp | I(from to) | RPM[840,1200,1590]
test_idle |  | 2 minutes nothing on | 250 | - | - | - | - | -
test_warmup |  | down 2 turns, then up to 1800 rpm, accelerometer frequency test at 1800, No load | 200
T20_Ten200_RPM1800_CompOn | 20 | running with compressor 1800rpm, fans on max | 200 | 210
T21_TenHighToLow_RPM1200 | 21 | up3.5 turns, starting on high tension(300) going down one turn down to very low, steady state pressure from 2, stop at 4, fans on max | 310
T22_TenHighToLow_RPM1200 | 22 | down 1 repeat, steady state pressure from 2, stop at 4 | 280
T23_TenHighToLow_RPM1200 | 23 | down 1 repeat, steady state pressure from 2, stop at 4 | 250
T24_TenHighToLow_RPM1200 | 24 | down 1 repeat, steady state pressure from 2, stop at 4 | 220
T25_TenHighToLow_RPM1200 | 25 | down 1 repeat, steady state pressure from 2, stop at 4 | 195
T26_TenHighToLow_RPM1200 | 26 | down 1 repeat, steady state pressure from 2, stop at 4 | 165
T27_TenHighToLow_RPM1200 | 27 | down 1 repeat, steady state pressure from 2, stop at 4 | 140
T28_TenHighToLow_RPM1200 | 28 | down 1 repeat, steady state pressure from 2, stop at 4 | 115
T29_TenHighToLow_RPM1200 | 29 | down 1 repeat, steady state pressure from 2, stop at 4 | 90
T30_TenHighToLow_RPM1200 | 30 | down 1 repeat, steady state pressure from 2, stop at 4 | 65
T31_TenHighToLow_RPM1200 | 31 | down 1 repeat, steady state pressure from 3, stop at 5 | 45
T32_TenHighToLow_RPM1200 | 32 | down 1 repeat, steady state pressure from 3, stop at 5 | >35 |  | 37
T33_LowTension | 33 | Ramping up with low tension, adding compressor changing load to high

## Test2018-05-09
Name | Test.nr | Description | T | T_after | T_Comp | T_after_comp | I(from to) | RPM
warmup
T34_AccOnComp_rpmLowToHigh | 34 | accelerometer on compressor right side, cable down, different rpm, up 4 turns, increasing load at 3:25, increasing to 1000 6:30, increasing to 1200 9:30, 12:15 up to 1400, up to 1600 at 15:50, up to 1800 at 18:50 comp off 22:50 | 150 |  |  |  | 21-22 | 810-1800
T35_EvapOutTest | 35 | Accelerometer back to tensioner arm , 1600rpm, comp on 2:50, trying for different evap_out, low load 5:00, 6:25 lowering evaporator fan, lowering again at 11:10, to lowest 12:50, 16:05 evap fan up, cond fan down, com off 21:50 | 150 | 130
T36TenHighToLowRPM1200HighLoadTen1 | 36 | 5 turns up, 2 more, high load all tension from 300 , steady state pressure, RPM condenser fan 730, RPM evaporator fan full | 300 |  |  |  | 23
T37TenHighToLowRPM1200NoLoadTen1 | 37 | tension 300 , no compressor | 300 |  |  |  | 10
T38TenHighToLowRPM1200NoLoadTen2 | 38 | tension 270 , no compressor, down one turn, temp steady state | 250 |  |  |  | 10
T39TenHighToLowRPM1200HighLoadTen2 | 39 | tension 270(250), compressor on in beginning , pressure steady state 6:00-9:00, ramp down in end | 250 |  |  |  | 23
T40TenHighToLowRPM1200HighLoadTen3 | 40 | down one, compressor on in beginning | 220 |  |  |  | 23
T41TenHighToLowRPM1200NoLoadTen3 | 41 | compressor off, ramp down in end | 220 |  |  |  | 10
T42TenHighToLowRPM1200NoLoadTen4 | 42 | compressor off down one, ramp up to 1200,up to steady state temp | 190 |  |  |  | 10
T43TenHighToLowRPM1200HighLoadTen4 | 43 | compressor on up to steady state, then off and ramp down | 190 |  |  |  | 23
T44TenHighToLowRPM1200HighLoadTen5 | 44 | down one, ramp up, compressor on, compressor turned off | 165 |  |  |  | 23
T45TenHighToLowRPM1200NoLoadTen5 | 45 | no comp, steadt state temp | 165 |  |  |  | 10
T46TenHighToLowRPM1200NoLoadTen6 | 46 | no comp, down one, ramp up, steady state temp at 6:00, ramp down | 140 |  |  |  | 10
T47TenHighToLowRPM1200HighLoadTen6 | 47 | comp started, ran until steady state pressure, then comp on, ramp down | 140 |  |  |  | 23
LUNCH BREAK
T48TenHighToLowRPM1200HighLoadTen7 | 48 | warm up cond fan rpm 730, down one turn, high load | 110 |  |  |  | 23
T49TenHighToLowRPM1200NoLoadTen7 | 49 | same, no load, compresor turned off in beginning, steady state, ramp down | 110 |  |  |  | 10
T50TenHighToLowRPM1200NoLoadTen8 | 50 | no comp, down one, ramp up, steady state temp, ramp down(?) | 85 |  |  |  | 10
T51TenHighToLowRPM1200HighLoadTen8 | 51 | high load, compressor on in beginning, steady state pressure, ramp down | 85 |  |  |  | 23
T52TenHighToLowRPM1200HighLoadTen9 | 52 | down one, ramp up, compressor on, steady state pressure | 70 |  |  |  | 23
T53TenHighToLowRPM1200NoLoadTen9 | 53 | compressor turned off, steady state temp, ramp down | 70 |  |  |  | 10
T54TenHighToLowRPM1200NoLoadTen10 | 54 | no comp, down one, ramp up, steady state temp | 45 |  |  |  | 10
T55TenHighToLowRPM1200HighLoadTen10 | 55 | compressor turned on, up to steady state pressure | 45 |  |  |  | 23
T56TenHighToLowRPM1200HighLoadTen11 | 56 | down one, ramp up, compressor on, steady state pressure | <35 |  | 55 |  | 23
T57TenHighToLowRPM1200NoLoadTen11 | 57 | compressor turned off, steady state temp, ramp down | <35 |  | 55 |  | 10
T58 RandomDriveTen11 | 58 | doing some random testing, fans, speed etc | <35 |  | 55
T59 CompOnOffTen11 | 59 | 10 off 20 on, started on 10 | <35 |  | 55
T60 CompOnOff5Ten5 | 60 | up 6 turns, 30 seconds to start, 20 on, 10 off, 4 times | 180
T61 CompOnOff5Ten1 | 61 | up 5 turns(320), down one turn, start on 40, 20 seconds on, 10 seconds off, 4 times | 290

## Changes to rig and DAQ
2018-04-27 | 14:38 | moved thermo couple on pulley
| 15:09 | card board is loose, warm air enters compressor area
| 15:41 | card borad back in place
2018-05-02 | 10:26 | board to lead condensor heat to the back